## Overview
Section | Priority | Estimated Hours
Setup & Architecture | Critical | 45h
Design System | Critical | 55h
Data Layer & API | High | 30h
Main Store Pages | High | 65h
Advanced Ecommerce | High | 55h
Authentication & Profile | High | 45h
Supermarket Module | Medium | 35h
SEO + PWA + Optimization | Critical | 65h
Testing & Stabilization | Medium | 30h
TOTAL | - | 380-420h

## Setup & Architecture
Task | Hours
Project Setup | 6h
Code Quality Tools | 5h
Axios Infrastructure | 6h
React Query Setup | 8h
NextAuth Setup | 10h
SVGR + Assets | 2h
Folder Architecture | 4h
Environment Config | 4h

## Design System
Task | Hours
Design Tokens | 10h
Typography & Colors | 6h
Base Components | 16h
Interactive Components | 10h
Layout Components | 8h
Responsive Foundation | 5h

## Data Layer & API
Task | Hours
Service Layer | 8h
Type Definitions | 8h
Mock API | 10h
Query Standards | 4h

## Main Store Pages
Task | Hours
Home Page | 16h
Shop Page | 18h
Product Page | 18h
Cart Page | 8h
Blog & Contact | 5h

## Advanced Ecommerce
Task | Hours
Filters | 20h
Realtime Search | 12h
Payment Flow | 15h
Search Dropdown | 8h

## Authentication & Profile
Task | Hours
Login/Register | 10h
Dashboard Layout | 8h
Profile Tabs | 12h
Orders & Favorites | 10h
Address Management | 5h

## Supermarket Module
Task | Hours
Supermarket Home | 10h
Cards & Sections | 10h
Mobile UX | 8h
Offer Sections | 7h

## SEO + PWA + Optimization
Task | Hours
Dynamic SEO | 15h
Structured Data | 8h
Sitemap & Robots | 5h
PWA Setup | 12h
Performance Optimization | 15h
Image Optimization | 10h

## Testing & Stabilization
Task | Hours
Responsive Testing | 8h
Auth Testing | 5h
API Edge Cases | 7h
Bug Fixes | 10h

## Sprint Plan
Sprint | Estimated Hours | Focus
Sprint 1 | 45h | Setup & Architecture
Sprint 2 | 55h | Design System
Sprint 3 | 50h | Data Layer + Shop Infrastructure
Sprint 4 | 65h | Main Store Pages
Sprint 5 | 45h | Cart + Payment
Sprint 6 | 45h | Auth + Profile
Sprint 7 | 35h | Supermarket
Sprint 8 | 55h | SEO + PWA + Stabilization